## Security Copilot UAT
User Story | What We Are Trying to Achieve | Repo References | Phase | Step | Done | Expected Results
As a SOC analyst, I want user-reported phishing emails autonomously triaged and classified as a real threat or a false alarm before they reach my queue, so I stop spending ~30 minutes reading false alarms. | Insert an autonomous LLM triage tier (Security Copilot Phishing Triage Agent) ahead of the analyst: auto-resolve false positives, keep true positives open and tagged with a transparent rationale. | TRAP-MDO-Migration/automation/security-copilot/01-phishing-triage-agent.md TRAP-MDO-Migration/automation/security-copilot/README.md TRAP-MDO-Migration/08-abuse-mailbox-and-user-reporting.md | Implementation | 1. Confirm MDO Plan 2 and a Security Copilot SCU entitlement (E5 inclusion or provisioned). | ⬜ | Benign report auto-resolved as False Positive with a plain-language rationale. Phish simulation classified True Positive; incident open with the Agent tag and a viewable decision-tree. Analyst queue shows only true positives.
|  |  | Implementation | 2. Enable Unified RBAC (URBAC) for Defender for Office 365. | ⬜
|  |  | Implementation | 3. Enable 'Monitor reported messages in Outlook' and the reported-phish alert policy. | ⬜
|  |  | Implementation | 4. Disable the 'Auto-Resolve - Email reported by user as malware or phish' tuning rule. | ⬜
|  |  | Implementation | 5. Run the agent setup wizard; assign an Entra Agent ID with the five Security operations permissions scoped to the MDO data source. | ⬜
|  |  | Implementation | 6. Run the agent in observe mode through the Phase 2 parallel run. | ⬜
|  |  | Test | 1. Submit one known-benign report and one known-phish simulation via the Report button. | ⬜
|  |  | Test | 2. Confirm the agent triggers on the reported-phish alert and self-assigns. | ⬜
|  |  | Test | 3. Open each incident and review the agent verdict, evidence, and decision-tree. | ⬜
|  |  | Test | 4. Confirm the false positive is auto-resolved and the true positive stays open and Agent-tagged. | ⬜
As a SOC analyst, I want to correct a wrong agent verdict in plain language and have the agent learn from it, so our organisation's context shapes future triage. | Provide a CLEAR-equivalent analyst tuning loop via stored, per-organisation feedback lessons. | TRAP-MDO-Migration/automation/security-copilot/01-phishing-triage-agent.md TRAP-MDO-Migration/03-trap-capability-matrix.md | Implementation | 1. On a misclassified alert, select 'Change classification'. | ⬜ | Lesson stored with status 'In use'. Subsequent matching alert classified per the lesson, with the lesson cited as evidence. All feedback logged for audit whether or not promoted to a lesson.
|  |  | Implementation | 2. Enter specific, contextual feedback (sender domain, subject pattern, recipient pattern). | ⬜
|  |  | Implementation | 3. Select 'Evaluate feedback' and review the generated lesson. | ⬜
|  |  | Implementation | 4. Select 'Use this feedback to teach the agent' and Save. | ⬜
|  |  | Implementation | 5. Seed initial lessons for finance, benefits, HR, and file-share sender domains. | ⬜
|  |  | Test | 1. Add a lesson, e.g. 'benefits mail must originate from @benefits.<our-domain>'. | ⬜
|  |  | Test | 2. Submit a new report that violates the lesson. | ⬜
|  |  | Test | 3. Open the feedback management page and check the lesson status. | ⬜
As a SOC analyst, I want a plain-language incident summary and next-best-action recommendations on each incident, so I cut read-in time and act faster. | Stand up the embedded read-side Copilot experiences (incident summarisation and guided response) in Defender XDR and Sentinel. | TRAP-MDO-Migration/automation/security-copilot/02-copilot-in-defender-and-sentinel.md TRAP-MDO-Migration/06-sentinel-soar-orchestration.md TRAP-MDO-Migration/05-defender-xdr-air-zap.md | Implementation | 1. Onboard Sentinel to the Defender portal so incidents unify. | ⬜ | One-paragraph summary fusing internal telemetry with Microsoft Threat Intelligence. Guided-response next-best actions listed against the incident. Executive report generated, suitable for a non-technical audience.
|  |  | Implementation | 2. Confirm Copilot in Defender is enabled for the tenant. | ⬜
|  |  | Implementation | 3. Open a phishing incident, generate the summary, and review guided response. | ⬜
|  |  | Test | 1. Open a representative phishing incident. | ⬜
|  |  | Test | 2. Generate the Copilot incident summary. | ⬜
|  |  | Test | 3. Request an executive (non-technical) incident report. | ⬜
As a SOC analyst, I want to express ad-hoc hunts in plain English and have Copilot generate the KQL against our tables, so long-tail hunts do not need hand-written queries. | Enable natural-language-to-KQL for Sentinel and Defender advanced hunting as an accelerator over the curated KQL library. | TRAP-MDO-Migration/automation/security-copilot/02-copilot-in-defender-and-sentinel.md TRAP-MDO-Migration/09-kql-detection-library.md | Implementation | 1. Configure a default Sentinel workspace for Copilot under Sources. | ⬜ | Valid KQL generated against EmailEvents / EmailUrlInfo and runs without error. Results return; analyst can refine and promote a good hunt into doc 09.
|  |  | Implementation | 2. Enable the 'Microsoft Sentinel (Preview)' and 'Natural language to KQL for Microsoft Sentinel (Preview)' plugins. | ⬜
|  |  | Implementation | 3. Prompt Copilot from the advanced-hunting surface. | ⬜
|  |  | Test | 1. Prompt: 'show all mail from sender X to VIP users in the last 3 days'. | ⬜
|  |  | Test | 2. Run the generated KQL. | ⬜
|  |  | Test | 3. Compare output to the curated Q-library equivalent in doc 09. | ⬜
As a SOC analyst, I want saved promptbooks for our recurring workflows, so triage and reporting are repeatable. | Operationalise the project promptbook library (PB-A..PB-F), each paired to a playbook P1-P7. | TRAP-MDO-Migration/automation/security-copilot/03-promptbook-library.md TRAP-MDO-Migration/10-logic-apps-playbook-library.md | Implementation | 1. In the standalone portal, refine each PB-x prompt set against a real incident. | ⬜ | Promptbook returns the structured investigation / report. Parameters fill cleanly; SCU cost per run is visible on the usage dashboard.
|  |  | Implementation | 2. Save each set as a promptbook using its PB-x name. | ⬜
|  |  | Implementation | 3. Parameterise inputs (IncidentId, NetworkMessageId, DLAddress, IOC). | ⬜
|  |  | Test | 1. Run PB-A (user-reported phishing investigation) on a true-positive incident. | ⬜
|  |  | Test | 2. Run PB-D (TI retroactive sweep) with a test IOC. | ⬜
As a security lead, I want to confirm our Security Copilot entitlement and size SCU capacity from real usage, so we adopt Copilot at predictable cost. | Adopt on E5 inclusion first and measure cost-per-email before provisioning any SCUs. | TRAP-MDO-Migration/automation/security-copilot/04-licensing-scu-governance.md TRAP-MDO-Migration/13-licensing-and-operations.md | Implementation | 1. Confirm the E5 inclusion allocation (400 SCUs/month per 1,000 paid E5 licences, capped at 10,000). | ⬜ | Documented SCU demand vs allocation. No provisioning required if demand is within the inclusion allocation; decision recorded in doc 13.
|  |  | Implementation | 2. Run the agent trial; read cost-per-email on the Performance tab. | ⬜
|  |  | Implementation | 3. Multiply by daily reported-mail volume; add embedded/promptbook usage from the usage dashboard. | ⬜
|  |  | Implementation | 4. Decide provisioned SCUs vs pay-as-you-go and record it in doc 13. | ⬜
|  |  | Test | 1. Export the usage-monitoring dashboard to Excel, filtered to agent operations. | ⬜
|  |  | Test | 2. Compute steady-state SCU demand and compare against the inclusion allocation. | ⬜
As a security admin, I want the autonomous agent to run under a scoped, least-privilege identity with full audit, so automation stays inside our governance model. | Run the agent under an Entra Agent ID with least privilege, Purview audit of every decision, and admin pause/remove control. | TRAP-MDO-Migration/automation/security-copilot/04-licensing-scu-governance.md TRAP-MDO-Migration/automation/security-copilot/01-phishing-triage-agent.md | Implementation | 1. Create a new Entra Agent ID during agent setup. | ⬜ | Agent holds only the five scoped permissions on the MDO data source. Every decision is in Purview audit with a viewable decision-tree. Pause/remove works; the oversight group can review all activity.
|  |  | Implementation | 2. Assign a role with only the five Security operations permissions, scoped to the MDO data source. | ⬜
|  |  | Implementation | 3. Give the oversight group permissions equal to or greater than the agent's. | ⬜
|  |  | Implementation | 4. Confirm decisions and feedback are written to Microsoft Purview audit. | ⬜
|  |  | Test | 1. Review the agent identity and role on the Defender Permissions page. | ⬜
|  |  | Test | 2. Verify agent decisions appear in Purview audit logs. | ⬜
|  |  | Test | 3. Pause the agent and confirm triage stops. | ⬜
As a SOC lead, I want confirmed low-risk phish to remediate without a human keystroke while VIP, irreversible, and novel cases still gate, so we eliminate toil but keep controls. | Add a conditional auto-approve rule between the agent's True-Positive verdict and the remediation playbooks, generalising the P2 watchlist short-circuit. | TRAP-MDO-Migration/automation/security-copilot/05-zero-touch-phishing-pipeline.md TRAP-MDO-Migration/automation/logic-apps/P2-ti-sweep-remediate/README.md TRAP-MDO-Migration/automation/logic-apps/P6-two-stage-approval-vip/README.md | Implementation | 1. Build a Sentinel automation rule between the agent TP verdict and the remediation playbook. | ⬜ | In-policy case soft-deleted with no human click and an incident comment posted. VIP case waits for two-stage approval (P6). Novel case is gated once, then automatic thereafter; auto-approve rate rises over time.
|  |  | Implementation | 2. Auto-approve only when the sender/URL/hash is on a KnownBad_* watchlist, no VIP is touched, and the action is reversible (soft-delete). | ⬜
|  |  | Implementation | 3. Route VIP, irreversible, or novel-campaign cases to the P6 two-stage human gate. | ⬜
|  |  | Implementation | 4. Promote judged novel campaigns to a watchlist entry or an agent lesson. | ⬜
|  |  | Test | 1. Fire a true positive matching a KnownBad watchlist with no VIP recipient. | ⬜
|  |  | Test | 2. Fire a true positive that touches a VIP/VAP watchlist member. | ⬜
|  |  | Test | 3. Fire a novel campaign with no prior watchlist or lesson match. | ⬜